HEAL-14: Project Plan, Schedule & Documentation Template

1. Project Charter

1.1 Project Overview

| Field | Project-specific information |
| --- | --- |
| Project Title | Healthcare Integration & Clinical Terminology Test Harness |
| Industry Partner | FAZ Australia Pty Ltd |
| Team Members | Rikesh Aryal, Charity Gwese, Sonam Pelden, Zubair Adil Soomro |
| Project Supervisor | Atif Nisar (CTO, FAZ Australia) |
| Date | 13 August 2026 |
| Unit | ICT942 — Cyber Security Project |
| Institution | Crown Institute of Higher Education (CIHE) |

1.2 Project Background

FAZ Australia is a Canberra-based health-technology company whose flagship product, MedTalk, is an AI clinical documentation platform. MedTalk Connect, FAZ Australia’s white-label interoperability platform, provides canonical FHIR APIs and connectors to clinic software (Best Practice via Halo Connect) and hospital systems (Oracle Health Millennium). Before MedTalk Connect updates reach production, they must be validated against realistic but entirely synthetic clinical environments to prevent data integrity failures, compliance breaches, or patient-safety incidents.

This project designs and builds a safe, fully synthetic test harness — a mock healthcare integration environment — that simulates the systems MedTalk Connect talks to. The harness will expose FHIR R4 endpoints, ingest simulated HL7 v2 messages, serve synthetic SNOMED CT-AU coded records, and execute automated tests including error injection (slow responses, malformed payloads, dropped connections). No real patient data will ever be used. The Stage 1 deliverable (due 23 August 2026) comprises the architecture, test-data plan, and written test plan; Stage 2 (Semester 2) will implement the live harness and automated suite.

1.3 Project Objectives (SMART)

| ID | Objective | Evidence of Completion | Source |
| --- | --- | --- | --- |
| OBJ-1 | By 23 August 2026, design and document a synthetic FHIR R4 test harness architecture simulating Best Practice (Halo Connect) and Oracle Health Millennium integrations, validated by mentor sign-off. | Approved architecture diagram and interface design document. | Project Brief / Roadmap |
| OBJ-2 | By 23 August 2026, create a curated synthetic SNOMED CT-AU test dataset (≥50 records) covering diabetes, hypertension, and asthma with corresponding ICD-10-AM and MBS mappings. | Test Data Plan with sample payloads and mapping tables. | Project Brief / Roadmap |
| OBJ-3 | By 23 August 2026, develop a written test plan covering happy-path, error-injection (slow/malformed/dropped), and SNOMED→ICD-10-AM/MBS edge-case scenarios, achieving ≥90% defined coverage. | Test Plan document with traceability matrix. | Project Brief / Roadmap |
| OBJ-4 | By 11 October 2026, deliver a complete Stage 1 design package (architecture, data plan, test plan) ready for Stage 2 build and demonstration. | Final design package committed to GitHub and presented to FAZ Australia. | 10-Week Roadmap |

1.4 Scope

| ID | In / Out of Scope | Description | Evidence |
| --- | --- | --- | --- |
| SC-01 | In | Synthetic FHIR R4 REST API mocking Best Practice (Halo Connect) and Oracle Health Millennium canonical endpoints. | Project Brief |
| SC-02 | In | Synthetic patient records coded in SNOMED CT-AU with ICD-10-AM and MBS mappings. | Project Brief |
| SC-03 | In | Automated test suite with pass/fail reporting and error-injection scenarios (slow, malformed, dropped). | Project Brief |
| SC-04 | In | Architecture diagrams, test data plan, and written test plan documentation. | Project Brief |
| SC-05 | In | HL7 v2.4 ADT/ORM/ORU message ingestion simulation over MLLP with ACK/NAK handling. | Starter Kit |
| SC-06 | Out | Connection to any real patient data or production clinical system. | Starter Kit §10 |
| SC-07 | Out | Production deployment, commercial hosting, or live integration with the real MedTalk platform. | Starter Kit §10 |
| SC-08 | Out | Mobile applications, full user authentication/identity systems, or production-grade security hardening. | Starter Kit §10 |
| SC-09 | Out | Epic connector implementation beyond sandbox-validated architecture references (Epic mock is architecture-only for Stage 1). | MOM 7 Aug |

1.5 Stakeholder Analysis

| ID | Stakeholder | Role | Needs / Interest | Influence | Engagement Method | Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| ST-01 | Atif Nisar (FAZ Australia) | Client / Sponsor / Mentor | Reusable, safe test environment; reduced connector bug risk; IP ownership of artefacts. | High | Weekly video call (Zoom/Teams); GitHub/Jira review | Project Brief |
| ST-02 | MedTalk Connect Engineers | End Users | A realistic sandbox to test connector changes before production; fast feedback on failures. | High | Demo sessions; technical documentation; Slack/Teams | Project Brief |
| ST-03 | CIHE / Readygrad | Academic Administrator | Compliance with WIL terms; student assessment; ethical conduct. | Medium | Moodle submission; supervisor feedback forms | Assessment Brief |
| ST-04 | Student Team (ICT942) | Developers | Clear requirements; mentor access; passing assessment; professional portfolio. | High | Daily standups; Jira assignments; GitHub PRs | Team Agreement |
| ST-05 | Canberra Health Services | Future Beneficiary | Safer MedTalk Connect deployments protecting real patient records. | Low | Indirect via FAZ Australia reference | MEDTAL_1 |
| ST-06 | Australian Digital Health Agency | Standards Body | Conformance to AU Core, FHIR R4, and SNOMED CT-AU national standards. | Medium | Public implementation guides; no direct contact | MEDTAL_1 §1.6 |

Power–Interest Matrix Strategy:

- High Power / High Interest (Atif Nisar, Student Team): Manage closely. Weekly demos, direct Jira access, immediate escalation path.

- High Power / Low Interest (CIHE/Readygrad): Keep satisfied. Submit documentation on time; maintain daily logbooks.

- Low Power / High Interest (MedTalk Engineers): Keep informed. Share GitHub commits and test reports; invite to demos.

- Low Power / Low Interest (Canberra Health Services): Monitor. Reference as business case only.

1.6 Success Criteria

| ID | Success Criterion | How Measured | Target | Source |
| --- | --- | --- | --- | --- |
| SC-01 | Architecture diagram approved by mentor. | Formal review meeting sign-off. | 100% approval by 23 Aug. | Project Roadmap |
| SC-02 | Synthetic dataset covers ≥50 patient records across ≥3 clinical conditions. | Record count in test data plan. | ≥50 records; ≥3 conditions. | Project Roadmap |
| SC-03 | Test plan defines ≥90% of planned test scenarios with acceptance criteria. | Traceability matrix coverage %. | ≥90% coverage. | Assessment Rubric |
| SC-04 | All code and docs in GitHub with clear README. | Mentor clones repo and reproduces setup unaided. | Successful unaided setup. | Starter Kit §9 |
| SC-05 | Supervisor invited to Jira and GitHub with visible individual contributions. | Platform access logs and commit history. | 4 members; regular commits. | Tutorial 1 |

2. Team Working Agreement

| Item | Agreed by Team |
| --- | --- |
| Communication channel | Microsoft Teams (primary); WhatsApp (urgent only) |
| Meeting frequency | Mentor check-in: weekly (day TBD via Doodle). Internal stand-up: Tuesday & Friday 19:00 AEST. |
| Expected response time | Chat: 24 hours. PR review: 48 hours. Mentor question: 48 hours. |
| Decision-making process | Technical decisions: team consensus (3/4 majority). Disputes: mentor tie-break. Assessment deadlines: unanimous agreement required. |
| File naming convention | HEAL-XX_short-description_v1.0_YYYY-MM-DD.docx (e.g., HEAL-18_SRS_v1.0_2026-08-13.docx) |
| Jira update rules | Update ticket status daily. Move to "Done" only after peer review and evidence link attached. Link every commit to Jira ID in comment. |
| GitHub commit expectations | Feature branches only. PR requires 1 approving review. Commit message format: HEAL-XX: Imperative description under 72 chars. No direct pushes to main. |
| Conflict escalation path | 1. Direct discussion between involved members. 2. Full team mediation within 24 hours. 3. Escalate to Atif Nisar. 4. CIHE supervisor if unresolved. |

3. Project Schedule (10-Week Roadmap)

| Week | Dates | Focus | Deliverable | Owner Lead |
| --- | --- | --- | --- | --- |
| Week 1 | 3–9 Aug | Project initiation & requirements analysis | Project charter, task allocation, timeline | Team Lead |
| Week 2 | 10–16 Aug | System analysis & SRS drafting | Requirements Specification (Version 1) | Integration Lead |
| Week 3 | 17–23 Aug | System architecture design | Initial Architecture Diagram | Team Lead |
| Week 4 | 24–30 Aug | FHIR interface design | FHIR Integration Design Document | Integration Lead |
| Week 5 | 31 Aug–6 Sep | Synthetic data design | Test Data Plan (Draft) | Clinical Data Lead |
| Week 6 | 7–13 Sep | Data mapping & validation | Data Mapping Document | Clinical Data Lead |
| Week 7 | 14–20 Sep | Test planning | Test Plan (Draft) | Testing Lead |
| Week 8 | 21–27 Sep | Review & refine designs | Complete Design Review Report | Testing Lead |
| Week 9 | 28 Sep–4 Oct | Documentation & QA | Finalised Stage 1 Documentation | Team Lead |
| Week 10 | 5–11 Oct | Final preparation & presentation | Final Design Package + Presentation | All |