Below is a 10-week project plan for Stage 1 (Design Phase) of the MedTalk project. It is designed for a team of four students, with responsibilities distributed so everyone contributes each week. The plan aligns with the Stage 1 deliverables:

- Architecture Diagram

- Test Data Plan

- Written Test Plan

- Requirements and Design Documentation

| Week | Objectives | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Weekly Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| Week 1 | Project initiation and requirements analysis | Review project brief and define scope | Research MedTalk workflows and integrations | Research FHIR, SNOMED CT-AU, ICD-10-AM, MBS | Create project plan, schedule and documentation template | Project charter, task allocation, timeline |
| Week 2 | System analysis | Analyse Best Practice and Halo Connect architecture | Research hospital EMR integration methods | Identify functional and non-functional requirements | Create requirements specification document | Requirements Specification (Version 1) |
| Week 3 | System architecture design | Design overall solution architecture | Design synthetic environment components | Identify external systems and interfaces | Create architecture diagrams using Draw.io/Visio | Initial Architecture Diagram |
| Week 4 | FHIR interface design | Research required FHIR resources (Patient, Encounter, Observation etc.) | Map MedTalk data flow to FHIR resources | Document API endpoints and message flow | Review Australian Digital Health standards | FHIR Integration Design Document |
| Week 5 | Synthetic data design | Design synthetic patient profiles | Create SNOMED CT-AU coding structure | Research ICD-10-AM and MBS mappings | Define data validation rules | Test Data Plan (Draft) |
| Week 6 | Data mapping and validation | Map SNOMED CT-AU to ICD-10-AM | Map SNOMED CT-AU to MBS billing codes | Identify edge cases and uncommon scenarios | Review mappings and validate consistency | Data Mapping Document |
| Week 7 | Test planning | Define functional test scenarios | Design negative/error test scenarios | Create performance and connection failure scenarios | Document expected outcomes and acceptance criteria | Test Plan (Draft) |
| Week 8 | Review and refine designs | Review architecture against requirements | Review FHIR mappings | Review synthetic datasets | Review test plan and update documentation | Complete Design Review Report |
| Week 9 | Documentation and quality assurance | Finalise architecture documentation | Finalise requirements document | Finalise test data documentation | Finalise test plan and perform peer review | Complete Stage 1 Documentation |
| Week 10 | Final preparation and presentation | Prepare architecture presentation | Demonstrate data design and mappings | Present testing strategy | Compile final report and presentation slides | Final Design Package and Presentation |

Team Responsibilities Throughout the Project

Team Member 1 – Project Lead & Architecture

- Project planning and coordination

- Requirements management

- Overall architecture design

- Final documentation review

Team Member 2 – Integration & FHIR Specialist

- Research Best Practice and Halo Connect

- Design FHIR interfaces

- API and data flow documentation

- Integration review

Team Member 3 – Clinical Data Specialist

- Design synthetic patient records

- SNOMED CT-AU coding

- ICD-10-AM mapping

- MBS mapping validation

Team Member 4 – Testing & Documentation Lead

- Develop test strategy

- Design test cases

- Risk analysis

- Compile final documentation and presentation

Stage 1 Deliverables by Week 10

| Deliverable | Description |
| --- | --- |
| Requirements Specification | Functional and non-functional requirements for the synthetic environment |
| Architecture Diagram | Complete system architecture showing MedTalk, Best Practice, Halo Connect, FHIR interfaces, and synthetic systems |
| FHIR Design Document | FHIR resources, API interactions, and message flow |
| Synthetic Test Data Plan | Design of synthetic patient records with SNOMED CT-AU codes |
| Data Mapping Document | Mapping between SNOMED CT-AU, ICD-10-AM, and MBS codes |
| Test Plan | Functional, integration, performance, and failure test scenarios |
| Risk Register | Project risks and mitigation strategies |
| Stage 1 Presentation | Summary of the design, architecture, and testing approach |

This schedule gives the team a clear progression from requirements gathering, through system and data design, to testing strategy and documentation, ensuring all Stage 1 deliverables are completed and ready for implementation in Stage 2.